PRISM-M Task Breakdown Structure (TBS)

AI-Assisted Restaurant & Hospitality Management Platform

Prepared By: Adhityan R

SmartX Technologies

PRISM Phase: M – Milestone Execution

Purpose

Convert the approved Modular Web Application with AI Microservices design into a structured execution plan. Each task is independently buildable, testable, reviewable, and traceable to the approved requirements.

1. References

The execution plan is based on the following approved PRISM artifacts:

- PRISM-P Problem Brief

- PRISM-R PRD-Lite

- PRISM-I Solution Options Matrix

- PRISM-S Design Document

2. Execution Objectives

The primary objective of this milestone is to implement the core modules of the AI-Assisted Restaurant & Hospitality Management Platform following the approved architecture and design.

At the end of this milestone, the following functionality shall be available:

- User Authentication

- Reservation Management

- Inventory & Wastage Tracking

- Staff Management

- Customer Feedback Management

- AI Recommendation Engine

- AI Analytics Dashboard

- Notification Service

- Reporting Module

- Admin Dashboard

Acceptance Objectives

- All Functional Requirements implemented.

- REST APIs operational.

- Database schema deployed.

- JWT Authentication enabled.

- Role-Based Access Control implemented.

- AI services integrated.

- Unit, Integration, and End-to-End tests completed.

- Deployment pipeline configured.

3. Milestone Scope

Included Components

- Authentication Module

- Reservation Module

- Inventory & Wastage Module

- Vendor Management

- Staff Management

- Attendance Tracking

- Customer Management

- Feedback Module

- AI Analytics

- Notification Service

- Reporting Dashboard

- Admin Dashboard

Excluded Components

- Mobile Applications

- Loyalty Program

- Online Food Ordering

- Kitchen Robotics

- IoT Inventory Sensors

- Blockchain Supply Chain

- Multi-country Franchise Support

4. Epic Breakdown

| Epic ID | Epic Name |
| --- | --- |
| E-01 | Project Setup & Environment |
| E-02 | Authentication & User Management |
| E-03 | Reservation Management |
| E-04 | Inventory & Wastage Tracking |
| E-05 | Staff & Attendance Management |
| E-06 | Customer Feedback & Sentiment Analysis |
| E-07 | AI Recommendation Engine |
| E-08 | Business Analytics Dashboard |
| E-09 | Notification Service |
| E-10 | Vendor Management |
| E-11 | Reporting Module |
| E-12 | Testing & Deployment |

5. Story Breakdown

E-01 Project Setup

S-01

Create Git Repository

S-02

Configure Django Project

S-03

Configure React Application

S-04

Configure PostgreSQL Database

S-05

Docker Environment Setup

E-02 Authentication

S-06

User Registration

S-07

JWT Login

S-08

Password Reset

S-09

Role-Based Access Control

E-03 Reservation

S-10

Create Reservation

S-11

Update Reservation

S-12

Cancel Reservation

S-13

Waitlist Management

S-14

AI Table Allocation

E-04 Inventor

S-15

Opening Stock

S-16

Purchase Entry

S-17

Consumption Tracking

S-18

Wastage Tracking

S-19

Reorder Alerts

S-20

Vendor Management

E-05 Staff

S-21

Employee Registration

S-22

Attendance

S-23

Shift Scheduling

S-24

Leave Management

E-06 Customer Feedback

S-25

Review Collection

S-26

Sentiment Analysis

S-27

Feedback Dashboard

E-07 AI

S-28

Demand Forecasting

S-29

Recommendation Engine

S-30

Food Wastage Prediction

S-31

Business Intelligence

E-08 Dashboard

S-32

Sales Dashboard

S-33

Inventory Dashboard

S-34

Reservation Dashboard

S-35

Executive Dashboard

E-09 Notification

S-36

Email Notification

S-37

SMS Notification

S-38

Reminder Scheduler

E-10 Reporting

S-39

Daily Reports

S-40

Weekly Reports

S-41

Monthly Reports

6. Task Breakdown (Core Section)

| Task ID | Description | Component | Acceptance Criteria | Test Type | Dependency | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| T-001 | Create Django Project | Backend | Project runs successfully | Unit | None | Backend Developer |
| T-002 | Setup PostgreSQL | Database | Database connected | Integration | T-001 | Backend Developer |
| T-003 | Configure JWT Authentication | Authentication | Login works securely | Integration | T-002 | Backend Developer |
| T-004 | Build Reservation APIs | Reservation | CRUD operations successful | API Test | T-003 | Backend Developer |
| T-005 | Develop Reservation UI | Frontend | Reservation screens operational | UI Test | T-004 | Frontend Developer |
| T-006 | Build Inventory APIs | Inventory | Stock updated correctly | API Test | T-003 | Backend Developer |
| T-007 | Inventory Dashboard | Dashboard | Live inventory visible | UI Test | T-006 | Frontend Developer |
| T-008 | Vendor Management | Inventory | Vendor CRUD works | Unit | T-006 | Backend Developer |
| T-009 | Staff Module APIs | Staff | Attendance working | Integration | T-003 | Backend Developer |
| T-010 | Feedback Module | Customer | Reviews stored | Integration | T-003 | Backend Developer |
| T-011 | AI Sentiment Service | AI | Reviews classified | Unit | T-010 | AI Engineer |
| T-012 | AI Recommendation Engine | AI | Recommendations generated | Integration | T-006 | AI Engineer |
| T-013 | AI Forecasting | AI | Demand predictions generated | Integration | T-006 | AI Engineer |
| T-014 | Notification Service | Notification | SMS & Email delivered | Integration | T-004 | Backend Developer |
| T-015 | Reporting Module | Reporting | Reports generated | End-to-End | All | Full Stack Developer |
| T-016 | Deployment | DevOps | Docker deployment successful | Deployment Test | All | DevOps Engineer |

7. Acceptance Criteria Mapping

| Requirement | Related Tasks |
| --- | --- |
| User Authentication | T-003 |
| Reservation Management | T-004, T-005 |
| Inventory Tracking | T-006, T-007 |
| Vendor Management | T-008 |
| Staff Management | T-009 |
| Feedback Analysis | T-010, T-011 |
| AI Recommendation | T-012 |
| AI Forecasting | T-013 |
| Notification Service | T-014 |
| Reporting | T-015 |
| Deployment | T-016 |

8. Dependency & Risk Analysis

Task Dependencies

- Authentication must be completed before all secured modules.

- Database must be configured before backend services.

- Backend APIs must be completed before frontend integration.

- AI modules depend on Inventory, Reservation, and Feedback modules.

- Notification Service depends on Reservation and Customer modules.

- Reporting depends on all business modules.

Critical Path

Project Setup → Database → Authentication → Core Modules → AI Services → Dashboard → Testing → Deployment

Risks

| Risk | Mitigation |
| --- | --- |
| Delayed API Development | Parallel frontend mock APIs |
| AI Model Delay | Rule-based fallback logic |
| Database Migration Failure | Version-controlled migrations |
| API Integration Issues | Swagger/OpenAPI testing |
| Deployment Failure | Docker rollback strategy |

9. Definition of Done (DoD)

A task is considered complete when:

- Source code implemented.

- Code reviewed.

- Unit tests passed.

- Integration tests passed.

- API documentation updated.

- Database migrations completed.

- Security validation completed.

- Performance verified.

- Documentation updated.

- CI/CD pipeline successful.

10. Milestone Checkpoints

| Milestone | Deliverable |
| --- | --- |
| M1 | Environment Setup Complete |
| M2 | Authentication Complete |
| M3 | Reservation Module Complete |
| M4 | Inventory Module Complete |
| M5 | Staff Module Complete |
| M6 | AI Services Complete |
| M7 | Dashboards Complete |
| M8 | Testing Complete |
| M9 | Production Deployment Ready |

11. Execution Notes

- Follow Git Flow branching strategy.

- Maintain modular architecture.

- Follow REST API standards.

- Ensure RBAC for every API endpoint.

- Log all critical transactions.

- Use Docker for local development.

- Use PostgreSQL as the primary database.

- Maintain coding standards and documentation.

- Monitor performance using Prometheus and Grafana.

- Conduct code reviews before merging to the main branch.

12. Approval

Execution Plan Approval

Approver(s): ______________________

Date: ______________________

Decision:

☐ Approved

☐ Changes Required

13. AI Gold Prompt Mapping (Mandatory)

13.1 Approved AI Tool(s)

Primary

- ChatGPT

Secondary

- Claude Code

- Gemini Code Assist

- GitHub Copilot

13.2 Gold Prompt – PRISM-M

ROLE

You are an Engineering Manager and Technical Lead at SmartX Technologies.

OBJECTIVE

Convert the approved PRISM-S Design Document into a detailed, independently executable Task Breakdown Structure that enables efficient development, testing, review, and deployment.

CONTEXT

- Company: SmartX Technologies

- Project Type: AI-Assisted Restaurant & Hospitality Management Platform

- Architecture: Modular Web Application with AI Microservices

- Technology Stack: React.js, Django REST Framework, PostgreSQL, Redis, Docker, Azure, Gemini AI

- Definition of Done

- Delivery Timeline and Team Structure

INPUTS

- Approved PRISM-S Design Document

- PRISM-R Acceptance Criteria

- Repository Structure

- Coding Standards

- Team Roles

INSTRUCTIONS

- Break work into Epics, User Stories, and Tasks.

- Ensure each task is independently buildable and testable.

- Map every task to approved acceptance criteria.

- Define ownership, dependencies, and testing strategy.

- Identify execution risks and mitigation plans.

- Keep tasks modular, measurable, and reviewable.

OUTPUT FORMAT

- Epic Breakdown

- Story Breakdown

- Detailed Task Table

- Acceptance Criteria Mapping

- Dependency Analysis

- Risk Analysis

- Definition of Done

- Milestone Checkpoints

13.3 Evidence for PRISM Gate (M4 → M5)

✅ Task Breakdown Structure Completed

✅ Epics Defined

✅ User Stories Completed

✅ Tasks Mapped to Acceptance Criteria

✅ Dependencies Identified

✅ Risks & Mitigations Documented

✅ Definition of Done Verified

✅ Execution Plan Approved